## Quick Reference
WMP GCC High Migration — Design Quick Reference
All settled design facts and decisions at a glance. Sources: gap register Resolved Decisions (G-01-G-64), the 8/25 discovery session, and the 8/26 document review. Updated 8/26/2026.
Engagement
Client | Wisconsin Metal Parts (WMP) — metal fabricator, DoD supply chain
Compliance driver | CMMC 2.0 Level 2 (NIST SP 800-171); CUI/ITAR handling; DFARS 252.204-7012
Compliance ownership | RPO: Bound Planet (Grant Burns). Compliance mapping/evidence out of Essendis scope; Essendis configures M365 per its own judgment
Users | 150 total: ~50 information workers; heavily shop-floor (~40 shop-floor devices need M365)
Sites | 3 locations; new third site occupied 8/1, operationally ready mid-November
Cutover goal | November 13-16, 2026 (target); November 20-23 backup. Single cutover weekend (confirmed in doc review 8/26; matches the Asana schedule)
Hypercare | 1 week post-migration; 2-hour response objective; intake via email and Teams; WMP runs user-facing support thereafter
Licensing partner | Essendis (order in progress; tenant created on licence delivery)
Post-handoff ownership | WMP owns operations, monitoring, change control, renewals, and all documentation
Tenant & Identity
Production email domain | wisconsinmetalparts.com
Initial tenant domain | Default *.onmicrosoft.us at setup (the 'wmparts.onmicrosoft.us' reference is wrong)
Directory sync | Entra ID Connect re-pointed from the commercial tenant to GCC High; identities keep syncing from on-prem AD; accounts created in AD
Sign-in method | Password hash synchronisation (PHS)
Device join model | Hybrid Azure AD Join; dual AD + Intune management; GPO retained for drive mappings and printers (supersedes pure-Entra-join plan; SOW review tracks WBS conflict)
On-prem AD end state | Remains: legacy app authentication; manufacturing/LOB systems and file services depend on it. AD retirement out of scope
On-prem MFA | RSA retained for desktop MFA on-premises
Admin model | No standing Global Admins — all PIM-eligible; separate cadm- prefixed admin accounts; tenant bootstrap account WMPGCCHADMIN@wisconsinmetalparts.com (renamed 8/26 to avoid collision with the WMPAdmin LAPS account); time-bound activation with MFA; Essendis access (Michael Schraepfer, Jeremy Cornwell) removed at handoff
Account lifecycle | Group-based licensing driven by AD-synced groups; JML processes WMP-owned
Licensing (150 users)
15x | M365 G5 FUSL GCCH (ADD-99035-COMM)
55x | M365 Business Premium (AAD-59343-COMM-2) + BP Defender Purview Suite GCCH (AAV-01856-COMM-2) + Teams Phone Standard GCCH (RFT-00001-COMM)
80x | M365 F3 GCCH (AAA-99952-COMM) + F5 Security + Compliance Add-on (91Q-00003-COMM)
Coverage | Entra ID P2, Defender for Endpoint P2, and Purview/Endpoint DLP entitlements across all tiers (BP GCCH + suite verified against public SKU documentation)
Security & Compliance Configuration
MFA methods | Microsoft Authenticator primary for all users incl. shop floor; YubiKey (FIDO2) fallback; admins passkey-in-Authenticator or YubiKey (phishing-resistant); SMS/voice disabled
Conditional Access | 10 policies incl. new 'Geo Block (non-US)' with Travelers exception group; policy 3 = compliant or hybrid-joined (macOS removed — no Macs); report-only rollout, then activate; exclusions: break-glass group + migration accounts; AvePoint via app registrations
Terms of Use | Entra ID Terms of Use with CA grant; all users; annual re-acceptance; WMP legal reviews; SOC contacts TBD in Appendix B
Defender for Office 365 | Strict preset; Safe Links (email/Teams/Office); Safe Attachments incl. SPO/OneDrive/Teams (quarantine); admin-only release; notifications to admin team until WMP names a mailbox
CUI protection | Single CUI sensitivity label, manual labeling; DLP blocks on the label across workloads; Endpoint DLP in scope; Purview Message Encryption deploying; Communication Compliance out
Audit | Unified audit log + mailbox auditing at tenant init; 90-day retention (CMMC minimum)
SIEM | Arctic Wolf (WMP's) needs GCC High visibility — WMP-owned; monitoring/alerting design out of engagement scope. Break-glass sign-in alerting decided (8/26): Microsoft Entra ID sign-in alert
Windows Endpoints
Baselines | Microsoft Security Compliance Toolkit baselines via Intune; versions pinned at configuration; deviations recorded
BitLocker | FIPS-compliant algorithm; no PIN; keys escrowed to Entra ID BEFORE encryption; used-space-only. Migration requires full decrypt then FIPS re-encrypt
Removable media | USB blocked in separate policy with exception group
App control | WDAC in audit mode; WMP tailors enforcement policy
Local admin | Users are not local admins; joiner-admin suppressed; Windows LAPS rotates WMPAdmin (30-day + after use); IT elevates via WMPAdmin
EDR | Defender for Endpoint P2; EDR block mode; tamper protection; servers out of scope; WMP manages post-handoff
Updates / attestation | Simple Windows Update rings; device health attestation (Secure Boot, TPM) required for compliance; minimum OS Windows 11; all policies scoped to all devices, pilot ring first
App deployment | NinjaOne (RMM), NOT Intune — NinjaOne pushes commands and packages
Provisioning | Autopilot device preparation for net-new/rebuilt devices only (classic Autopilot unavailable in GCC High); existing fleet converts in place
Device conversion | ForensIT profile mapping executed via an RMM-pushed package or by an analyst with a USB stick — no migration waves (eliminated per 8/26 review); devices can be brought in-office if required; app redeployment via NinjaOne
Mobile (Intune MDM)
Fleet | Greenfield: no corporate mobiles today; planned under 40 devices, iOS + Android; no BYOD
Prereqs | Apple Business Manager and Android Enterprise not yet configured — set up before rollout (timing under evaluation)
Apps | Outlook, Teams, OneDrive, RSA Authenticator, Keeper; Essendis dictates app-protection settings
Out of scope | Device refresh/retire process; MAM-only path dropped
Teams Voice (CallTower)
Model | Direct Routing via CallTower (decided); SBC FQDN + certificate ownership settled during integration
Phones | 55 Teams Phone Standard + 15 included in G5; no phone service for the 80 frontline users
E911 | Delivered and configured by CallTower; WMP validates per-site test calls as part of CallTower service validation (8/26 review)
Rooms | 5 conference rooms (+ more at new site) keep current AV pattern; NO Teams Rooms in scope
Inventory | Number/DID inventory + porting LOA produced during CallTower pre-integration
Migration
Tool | AvePoint Fly (SaaS, Azure East US); Commercial-to-GCC High supported; source Global Admin available; single cutover event
Mail scope | Mailboxes already in commercial EXO; ~20 PST archives (~50 GB) merged into active mailboxes; no third-party archive
Collab scope | 5 confirmed SharePoint sites + departmental additions under evaluation; chat/channel migration confirmed; Planner/Forms/Viva/Power Automate/Power Apps/Power BI out of scope
Integrations | NinjaOne, Keeper, Fortra re-consented against GCC High; Pipedrive validated post-cutover; no apps authenticate via M365 today
DNS | Hosted at AWS, managed by WMP; TTL to 30 min from 5 days out; <1 hr domain-release gap at cutover
SMTP relay | Printers/MFPs, Epicor ERP, help-desk platform; authenticated submission with TLS where supported
External sharing | Guests today = SharePoint file sharing; objective: replace Kiteworks with SharePoint external sharing for CUI; free/busy with two sister orgs under research
Exchange Decommission
Reality | On-prem Exchange 2016 is a MANAGEMENT platform only — mailboxes/mail flow moved to M365 previously; decommission = hybrid-config + management-server removal
Sequencing | In flux — leaning post-cutover
Gate | 7-day monitored hold; authorization signed by Kyle Manderfield
After | Recipient management WMP-owned via Entra Connect/AD attributes; no Essendis runbooks
Networking & Infrastructure Facts
Wi-Fi | Two sites guest-only today; new site 3 gets corporate Wi-Fi via RADIUS (NPS or ClearPass)
PKI | On-prem PKI in place (device certs + NAC); keep-or-replace under evaluation
VPN | FortiGate SSL VPN + FortiClient EMS (~34 remote users, 1 fully remote); M365 auth integration desired; site-to-site VPNs between sites
File/print | 3 file servers reducing to 2 (~7 TB, UNC, no DFS); 2 print servers; drive maps + printing via GPO (Kyocera MyPrint under evaluation); file-server migration out of scope
ERP | Epicor ERP in Azure Government — Epicor-managed, WMP is tenant owner of record, no direct Azure admin access; separate-vs-combined tenant decision open (Asana)
Backup | ArcServe does not support GCC High; replacement evaluation is WMP-owned; M365 backup out of scope (native retention accepted)

## All Decisions
ID | Category | Item | Decision / Recorded Answer | Follow-through
G-01 | Endpoint & Device Management | Endpoint security baselines are absent from the design | Decision already taken (not yet in the document): Microsoft Security Compliance Toolkit baselines deployed via Intune. This must be written into the design, reconciled with WBS 4.3.1's "MDM Security Baseline" wording, and pinned to specific baseline versions. | Decision: Microsoft Security Compliance Toolkit baselines deployed via Intune. Essendis selects the concrete baseline set and pinned versions at configuration, reconciles the WBS 4.3.1 'MDM Security Baseline' wording, and maintains the deviation record for CMMC evidence.
G-02 | Program & Scope | GCC High tenant procurement is assumed complete | Essendis is licensing partner, order in progress. Tenant will be created when licenses delivered. | Essendis is the licensing partner; the order is in progress and the tenant is created when licences are delivered. Schedule anchors to licence delivery; Essendis records eligibility/provisioning facts in the design as they land.
G-03 | Program & Scope | Azure infrastructure was removed from scope, but the document still depends on Azure in several places: break-glass alerting via "Log Analytics in Azure", CA policy 5 (Azure Management / Azure Portal), PIM covering "Azure resources" and Azure RBAC Owner/Contributor, and Deployment phase 1 "Define Azure RBAC model" | Resolved - Known: Azure infrastructure was removed from scope; this is an M365-only design. The residual Azure references are leftovers from the prior revision and need to be removed or replaced with M365-native equivalents. | Azure infrastructure remains out of design scope; Essendis removes or replaces the residual Azure references (CA policy 5, PIM Azure RBAC wording, Deployment phase 1) with M365-native equivalents. Note: an Azure subscription does exist (see G-52) and may host Log Analytics for alerting only.
G-04 | Program & Scope | Migration schedule is undefined: cutover dates are listed as "TBD", the stated duration ("approximately 12 weeks | WMP (8/24): early-mid november - suggest available weekends. Confirmed 8/25: cutover goal is mid-November. (The Asana board's 'cutover holds at 12/4-7' note is stale - update the board.) | Cutover targeted for early-to-mid November. Essendis proposes candidate weekends (avoiding Thanksgiving week), names the pilot batch in the migration plan, updates the stale 'first week of May' schedule text, and commits dates to CallTower and the communications plan.
G-05 | Program & Scope | End state of the source Microsoft 365 Commercial tenant is undefined — the design ends at cutover and never says what happens to the commercial tenant or the CUI left in it | Entra connect should be disabled from old tenant, but then it will be left for customer to decom fuilly. | Config action: disable Entra Connect against the commercial tenant at cutover; WMP decommissions the old tenant fully thereafter.
G-06 | Licensing | No licensing design exists | WMP (8/24) licensing plan received: M365 G5 FUSL GCCH x15 (ADD-99035-COMM) M365 Business Premium x55 (AAD-59343-COMM-2) BP Defender Purview Suite GCCH x55 (AAV-01856-COMM-2) Teams Phone Standard GCCH x55 (RFT-00001-COMM) M365 F3 GCCH x80 (AAA-99952-COMM) M365 F5 Security + Compliance GCCH Add-on x80 (91Q-00003-COMM) = 150 users: 15 G5 / 55 BP tier / 80 F3 + F5 S&C. VERIFIED (public sources, 8/24): M365 Business Premium is offered in GCC High (announced Nov 3, ~300-seat cap; Microsoft SKU AAU-59343 matches the quote's AAD-59343 line). The combined Defender + Purview Suite GCCH add-on (AAV-01856 line) adds Entra ID P2, Defender for Endpoint P2, Defender for Office 365 P2, Defender for Identity/Cloud Apps, E5 Information Protection (auto-labeling, unified DLP incl. Endpoint DLP), Insider Risk, eDiscovery Premium, extended audit. With G5 (15) and F5 Security+Compliance (80), Entra ID P2 covers all 150 users; risk-based CA policies 7-8 are licensed tenant-wide. | Licensing plan adopted as quoted: 15x G5, 55x Business Premium + Defender/Purview Suite GCCH + Teams Phone Standard, 80x F3 + F5 Security & Compliance (verified against public GCC High SKU documentation; Entra ID P2 tenant-wide). Third-party seats (AvePoint Fly, ForensIT, CallTower service) and the commercial-overlap wind-down are handled in procurement.
G-07 | Licensing | Entra ID P2 purchase vehicle | Settled by the licensing plan: P2 arrives via M365 G5 (15 users) and the F5 Security + Compliance add-on (80 users); the 55-seat BP + Defender/Purview Suite tier's P2 entitlement is verified under G-06. | No purchase decision remains: Entra ID P2 is confirmed licensed for all 150 users — G5 (15), BP + Defender/Purview Suite GCCH (55), F5 Security + Compliance add-on (80). Verified against public SKU documentation 8/24.
G-08 | Identity & Access | No Entra ID Connect design | WMP (8/24): repointing sync to gcch Pure Entra ID join decided (G-09): sign-in is PHS alone; Seamless SSO drops out. | Existing Entra Connect is re-pointed to GCC High; sign-in is PHS alone (pure Entra join, Seamless SSO dropped). Essendis engineers the re-point sequencing, object matching, sync scope, and break-fix plan in the migration plan.
G-09 | Identity & Access | Device join model (design/WBS contradiction) | REVISED at discovery (8/25): the intended device strategy is Hybrid Azure AD Join with dual AD + Intune management; GPO remains in use (drive mappings, printers); RSA is retained for on-premises desktop MFA. This supersedes the earlier 'pure Entra join' answer. | Design update: device join model is Entra hybrid join; CA policy 3 keeps 'compliant or hybrid-joined'; the earlier Seamless-SSO-removal and CA-simplification actions are ON HOLD; the WBS/board 'Modern Workspace - Entra join & GPO retirement' phase conflicts with this and is addressed by the SOW-review action (Asana).
G-10 | Identity & Access | No statement of what remains on-premises after Exchange decommission and GPO retirement | legacy app authentication. AD retirement not in scope. | Design note: on-premises AD remains solely for legacy application authentication; AD retirement out of scope.
G-11 | Identity & Access | Authentication method design is contradictory and incomplete: the document states "All users will use the Microsoft Authenticator app", while CA policies 2 and 4 call for phishing-resistant authentication strength for admins | WMP (8/24): Admins should use passkey in authenticator or Yubikey WMP (8/24): shop-floor MFA = Microsoft Authenticator, with YubiKey as fallback. Discovery (8/25): RSA is retained for on-premises desktop MFA; the RSA Authenticator app deploys to mobile devices. | MFA methods: admins use passkey in Authenticator or YubiKey; all other users Microsoft Authenticator with YubiKey fallback, including shop floor. Essendis plans pre-cutover registration (TAP or on-site sessions) in the communications plan, sizes the YubiKey purchase from the fallback-user list, and leaves SMS/voice methods disabled.
G-12 | Identity & Access | No account lifecycle (joiner/mover/leaver) design | WMP (8/24): Licensing should be group based. Accounts created in AD and synced. | Accounts are created in on-premises AD and synced; licensing is group-based. Essendis documents the licence groups and the joiner/leaver runbook in the admin procedures (WBS 5.6.5).
G-13 | Identity & Access | Administrative role model is stated in principle only — "built-in roles | WMP (8/24): Exact user lists TBD. No standing global admin for admins, all will use PIM. Separate user and cadm- prefixed accounts. Mike and Jeremy from Essendis, and they're removed at handoff. | Admin model: no standing Global Administrators — all elevation via PIM; separate cadm- prefixed admin accounts; Essendis access (Mike, Jeremy) removed at handoff. The role list is finalised at implementation; Essendis sets PIM activation defaults (time-bound, MFA on activation).
G-14 | Conditional Access | Nine CA policies are specified but the rollout method is not: no report-only staging, no pilot group, no exclusion model beyond break-glass, and no service-account handling | WMP (8/24): deployed in report-only while verified, then activated. Break glass accounts group excluded along with migration accounts. Avepoint uses app registrations. | CA policies deploy in report-only until verified, then activate. Exclusions: break-glass group and migration accounts; AvePoint authenticates via app registrations. Essendis defines the report-only exit check in the runbook and corrects Deployment phase 1's 'security defaults' wording.
G-15 | Conditional Access | Named locations are named but not defined: the document lists "WMP HQ" and "Tool Crib" — two entries for a company with three physical locations — and gives no IP ranges, no egress detail, and no VPN posture | WMP (8/24): Sites TBD. Tool crib reference should be removed as specific to another customer. | Site names and egress IP ranges are collected at implementation and entered into the named locations; the 'Tool Crib' entry (another customer's artifact) is removed from the design.
G-16 | Conditional Access | The Locations section references a Conditional Access policy named "Geo Block (non-US)" and says to see the Conditional Access section — but no such policy exists in the nine defined policies | geoblock outside of US and add a travelers exception group. | Design/config action: add CA policy 10 'Geo Block (non-US)' with a Travelers exception group (fixes the dangling reference).
G-17 | Conditional Access | The Terms of Use / CUI warning in Appendix B is written but never wired to anything — no Conditional Access policy grants on Terms of Use acceptance, and the Entra ID section cross-references it to "Appendix A", which is the password matrix | WMP (8/24): yes, and applies to everyone. Reaccept annually. WMP will review. SOC addresses TBD. Correct any bad references. | Terms of Use delivered via Entra ID Terms of Use with a CA grant, applied to everyone, annual re-acceptance; WMP legal reviews the wording; bad cross-references corrected. SOC contact details are inserted into Appendix B when WMP establishes them.
G-18 | Exchange Online & Mail Flow | Application and device mail flow has no design | Discovery (8/25): senders are printers, the Epicor ERP, and the help-desk platform; TLS expected for supported devices; Pipedrive sends marketing/mailing-list mail via integration with the email platform. | Essendis designs authenticated SMTP relay per sender class against Exchange Online GCC High (TLS where supported), and validates the Pipedrive integration after cutover.
G-19 | Exchange Online & Mail Flow | Defender for Office 365 coverage is partial: the design defines Safe Attachments, anti-phishing, anti-malware, and anti-spam for email, but never mentions Safe Links (WBS 2.5.2) or Safe Attachments for SharePoint, OneDrive, and Teams (WBS 2.5.3) | WMP (8/24): Yes. Yes, quarantined. Strict. Admin release only. TBD who receives notifications. | Defender for Office 365: Strict preset policies; Safe Links everywhere and Safe Attachments for SPO/OneDrive/Teams (flagged files quarantined); quarantine release is admin-only. Notification recipients default to the admin team until WMP names a monitored mailbox.
G-20 | Exchange Online & Mail Flow | Room and resource mailboxes are undefined | Discovery (8/25): five conference rooms today with more planned at the new facility; no special booking regimes surfaced; no Teams Rooms planned. | Room/equipment mailboxes are created fresh in GCC High at configuration (per WBS 5.2.5); calendar history rebuilds clean.
G-21 | Collaboration Workloads | How WMP collaborates with the outside world after go-live is undefined | Discovery (8/25): guest accounts are used mainly for SharePoint file sharing, not Teams; Kiteworks currently handles external CUI exchange and the objective is to replace it with SharePoint external sharing; free/busy sharing with two sister organisations should be preserved if possible; Purview Message Encryption is being deployed. | Essendis designs the SharePoint external-sharing model for CUI (Kiteworks replacement — Asana research item); the external allow list is built from the sister orgs and partners at implementation; cross-tenant free/busy feasibility is an Asana research item.
G-22 | Collaboration Workloads | Site and team provisioning governance is missing, and the SharePoint section twice says "see the appendix for a list of sites that will be migrated" — there is no such appendix (the document contains only Appendix A, password matrix, and Appendix B, terms of use) | Discovery (8/25): five SharePoint sites confirmed for migration; departments are evaluating additional Teams/SharePoint assets; some assets belong to M365 Groups, others were created independently. | Migration list = the five confirmed sites plus departmental additions (Asana action tracks the evaluation); provisioning governance set at configuration.
G-23 | Collaboration Workloads | OneDrive client configuration is thin and one setting is incompatible with the target state: the design restricts sync to "PCs joined to specific domains", which relies on an AD domain GUID — but WBS 7 removes those endpoints from the domain | restrict by tenant ID. Silently before device migraton.Depends on license but It should be enough for users.Retention out of scope. | Config action: OneDrive sync restricted by GCC High tenant ID; Known Folder Move enabled silently before device migration; quota per licence; leaver-retention handling out of scope.
G-24 | Endpoint & Device Management | There is no Windows endpoint configuration design | WMP (8/24): No PIN, need FIPS algo, escrow keys to Entra before encrypting, encrypt used space, block USB media in separate policy w/ exception group, Simple Windows Update setup. Device health required else noncompliant. Everything scoped to all devices. Pilot ring members TBD. | Windows endpoint decisions: BitLocker with FIPS-compliant algorithm, no PIN, keys escrowed to Entra before encryption, used-space-only encryption; USB media blocked in a separate policy with an exception group; simple Windows Update ring setup; device health attestation required for compliance; everything scoped to all devices. Remaining profile values derive from the SCT baselines (G-01); the pilot ring is named at implementation.
G-25 | Endpoint & Device Management | Windows provisioning is unresolved | Correction to record in the design: classic Windows Autopilot is not available in GCC High — Autopilot device preparation is the available path. The existing fleet is converted in place with ForensIT (WBS 7.2), so Autopilot applies only to net-new and rebuilt devices. | Correction recorded: classic Autopilot is unavailable in GCC High — Autopilot device preparation is the path for net-new and rebuilt devices; the existing fleet converts in place with ForensIT (WBS 7.2). WBS 4.1.2/7.1.5 re-planned accordingly.
G-26 | Endpoint & Device Management | Local administrator rights and Windows LAPS are not addressed anywhere in the design or the WBS | Users will not be local admin Device joiner should not be local admin. LAPS will be configured with WMPAdmin user to rotate password every 30d or after it's been used. Account management policy in place to keep only WMPAdmin account in Local Administrators. IT admins will be able to elevate using WMPAdmin. no legacy apps needing kerberos or admin rights have been identified. | Config action: users are not local admins; joiner-admin suppressed; Windows LAPS rotates WMPAdmin (30-day and after use); account-management policy keeps only WMPAdmin in local Administrators; IT elevates via WMPAdmin.
G-27 | Endpoint & Device Management | Application control is committed to in WBS 4.3.5 (AppLocker/WDAC, CMMC CM.2.061) but has no design, no policy model, and no application inventory behind it | WDAC in audit mode to allow customer to create tailored WDAC policy. | Config action: deploy WDAC in audit mode; WMP tailors and enforces its own policy afterwards.
G-28 | Endpoint & Device Management | Microsoft Defender for Endpoint appears only in the WBS (2.5.5, "confirm licensing") and never in the design — no plan selection, no onboarding method, no alert routing, no coverage decision for servers | Defender for Endpoint P2. Licenses to be attached. EDR in block mode, tamper protection enabled. Servers out of scope. WMP managing after handoff. | Config action: Defender for Endpoint P2, EDR block mode, tamper protection on; servers out of scope; WMP manages after handoff. Licences arrive with the G-06 quote.
G-29 | Endpoint & Device Management | Group Policy is never mentioned in the design, yet WBS 4.2 requires a full GPO export, a GPO-to-Intune equivalence mapping, and a documented list of settings that cannot be replicated — and WBS 7.3 retires GPO entirely | Known from WBS 4.2: the gap analysis, equivalence mapping, and exceptions list are already committed deliverables, with exceptions flagged for customer decision and POA&M. | GPO export, Intune equivalence mapping, and the exceptions list proceed as committed in WBS 4.2 during the Intune workstream; exceptions go to WMP decision/POA&M; GPO unlink sign-off per WBS 7.3.
G-30 | Endpoint & Device Management | Certificate and network-access dependencies are undefined | Discovery (8/25): an on-premises PKI is in place (device certificates and NAC); FortiGate SSL VPN with FortiClient EMS (~34 remote users, one fully remote), M365 auth integration desired post-migration; two sites have guest-only Wi-Fi; the new third site gets corporate Wi-Fi via RADIUS (NPS or ClearPass), operational mid-November; site-to-site VPNs link the sites and the Azure Government ERP. | Essendis designs FortiGate/Entra authentication integration; site-3 Wi-Fi design aligns to the PKI keep-or-replace decision (Asana research item).
G-31 | Endpoint & Device Management | Shared and kiosk workstations on the shop floor are not addressed | Discovery (8/25): user population is heavily shop-floor with ~50 information workers; shared shop-floor PCs exist but WMP is moving to individual sign-ins; ~40 shop-floor devices need M365 access. | Design assumes individual credentials on the floor; ~40 shop-floor devices included in Intune scope and the F3 licence tier.
G-32 | Endpoint & Device Management | CA policy 3 asserts macOS as a managed device platform, but no macOS management, compliance policy, or enrolment path exists anywhere in the design or the WBS, and no Mac inventory has been taken | No mac - remove macos from CA policies. | No macOS devices exist: Essendis removes macOS from the CA policy 3 platform list (design edit).
G-33 | Endpoint & Device Management | Mobile fleet inputs are outstanding: the design records device counts by platform as TBD, leaves the MAM-only access path as an explicitly open item, and does not define which applications beyond Outlook and Teams are deployed or what the loss/wipe process is | Discovery (8/25): no corporate mobile devices today; planned deployment under 40 devices across iOS and Android; no BYOD; apps: Outlook, Teams, OneDrive, RSA Authenticator, Keeper; Apple Business Manager and Google Android management are not yet configured. | MDM section updated to a greenfield rollout with the five named apps; ABM/Android-platform setup timing and the platform-mix recommendation are Asana research items.
G-34 | Teams Voice | The telephony connectivity model is an open decision — Direct Routing and Operator Connect are both still on the table pending CallTower's GCC High confirmation | WMP (8/24): Direct routing via CallTower. Cost not in scope for this doc. | Teams Phone delivered via CallTower Direct Routing (cost out of design scope). Essendis obtains CallTower's GCC High Direct Routing specification and settles the SBC FQDN domain and certificate ownership during integration.
G-35 | Teams Voice | The numbering inventory the design commits to producing does not yet exist, and the surrounding commercial facts are undefined: current carrier and contract, who signs the porting Letter of Agency, and which of the ~150 users actually receive a DID | Licensing plan implies phone service for the 55 BP-tier users (Teams Phone Standard) plus the 15 G5 users (included in G5); the 80 frontline users get no phone service. | Number/DID inventory, carrier facts, and the porting LOA are produced during CallTower pre-integration planning as the design commits; licensing already fixes the phone population (55 BP-tier + 15 G5; no frontline phones).
G-36 | Teams Voice | Voice endpoints are not inventoried | Discovery (8/25): five conference rooms (more at the new facility) using dedicated Windows devices or user laptops with existing AV; no Teams Rooms deployment planned. | Design records no Teams Rooms in scope; rooms continue the current AV pattern.
G-37 | Teams Voice | Emergency calling is defined at site level only | out of scope - handled by calltower | Emergency calling (E911) is delivered and configured by CallTower; Essendis validates the per-site test calls per WBS 8.3.5.
G-38 | Data Migration | Source-side migration prerequisites are not captured: source tenant administrative access, the AvePoint Fly deployment model, tenant-to-tenant app consent, and confirmation that Fly supports a Commercial-to-GCC High cross-cloud move at all | Yes it's supported. Global admin access available for whole migration. Avepoint SaaS in Azure East US. Forget app registration consent and throttling. | No further action: Fly supports Commercial-to-GCC High; source Global Admin available for the whole window; AvePoint SaaS runs in Azure East US; app-consent/throttling tracking waived by WMP.
G-39 | Data Migration | Source data volumes and mailbox inventory are unquantified | Discovery (8/25): ~20 PST archives (~50 GB combined) to merge back into active mailboxes; no third-party mail archive beyond backups; WMP can rapidly support discovery once instructions arrive, and custom scripts require review before execution. | PST ingestion into mailboxes is added to the migration plan; mailbox/site sizing comes from the AvePoint discovery scan once scripts are provided and approved (Asana action).
G-40 | Data Migration | Coexistence during the migration window is not designed | One cutover event. | Design input: single cutover event — coexistence window minimal, no cross-tenant free/busy or Teams federation needed.
G-41 | Data Migration | Domain transition mechanics are missing | Discovery (8/25): production email domain is wisconsinmetalparts.com; the default *.onmicrosoft.us initial domain is acceptable at setup. The 'wmparts.onmicrosoft.us' value on the Asana board is wrong and must not be kept. | Design records wisconsinmetalparts.com as the primary SMTP/vanity domain and the default onmicrosoft.us as the initial domain; correct the erroneous tenant strings in the design ('.microsoftonline.us') and on the Asana board.
G-42 | Data Migration | Migration scope beyond mail, files, and Teams content is undefined, and the design over-promises in one place: it lists "Chat History" as included while WBS 5.3.3 qualifies it as "where supported by tooling" | Yes. Planner/Forms/Viva/Power Automate/PowerApps/PowerBI not in migration scope. | Design input: chat/channel migration confirmed supported; Planner, Forms, Viva, Power Automate, Power Apps, Power BI are out of migration scope.
G-43 | Data Migration | There is no application integration inventory | Discovery (8/25): no applications authenticate through M365 today (long-term goal: move several to Entra ID); NinjaOne, Keeper, and Fortra access mailboxes/calendars; service accounts are on-premises in a dedicated OU; multiple LOB and manufacturing systems authenticate against AD. | Re-consent NinjaOne/Keeper/Fortra integrations against GCC High at migration; the OU and service-account inventory is an Asana action; Entra ID app-auth adoption is a post-migration roadmap item.
G-44 | Data Migration | On-premises file shares are not mentioned anywhere | fileserver migration out of scope | Scope decision: on-premises file-server migration out of scope.
G-45 | Data Migration | The communications plan lists five message types but no detail, and end-user training is not addressed at all — while WBS 2.8.5 explicitly flags CUI labelling training as out of Essendis scope and hands it to WMP | WMP (8/24): Essendis writes, WMP approves and sends on TBD schedule. No training in scope. Communication details to be determined. | Communications: Essendis writes, WMP approves and sends; no end-user training in scope. Essendis drafts the communications package including day-of-cutover instructions; dates are set once the November weekend is fixed (G-04).
G-46 | Device Migration | Device inventory is missing | Servers are out of scope for Defender/Intune per WMP (G-28). | Windows device inventory by site/type is collected by WMP during pre-migration device preparation (WBS 7.1.1); Windows 11/TPM exceptions are handled wave-by-wave; servers remain out of scope (G-28).
G-47 | Device Migration | The ForensIT profile conversion is described in six bullets with no execution detail: no per-device runbook, no handling of credential and encryption state, and no treatment of the application-level breakage that a domain-to-Entra identity change causes | Discovery (8/25): all devices can be brought into the office for migration/encryption work; NinjaOne is the RMM and can push commands and packages; application deployment continues through NinjaOne rather than Intune; conversion requires full decrypt before FIPS re-encryption. | Conversion runbook: in-office waves executed/scripted via NinjaOne; application redeployment via NinjaOne (Intune app deployment descoped accordingly); decrypt/re-encrypt time boxed per wave.
G-48 | Device Migration | Access to on-premises resources from Entra-joined devices is unaddressed | Discovery (8/25): two print servers; three file servers reducing to two (~7 TB, UNC paths, no DFS); drive mappings deployed via GPO; printer management remains GPO-based (Kyocera MyPrint under evaluation); hybrid Azure AD Join is the intended device strategy, so AD Kerberos access continues. | With hybrid join, on-premises file/print access continues over AD Kerberos and drive maps/printing stay GPO-delivered; the WBS/board 'GPO retirement' phase is superseded pending the SOW review (Asana action).
G-49 | Exchange Decommission | The pre-decommission gate lists what must be true but not how it is proven | WMP (8/25, via chat): 7-day monitored hold; Kyle Manderfield signs the decommission authorization. Discovery (8/25): decommission sequencing is in flux - leaning post-cutover (as the design documents). Material reframing: on-prem Exchange 2016 is a MANAGEMENT platform only - all mailboxes and mail flow moved to M365 commercial previously - so decommission is hybrid-config/management-server removal, not a mail migration. | Design update: the pre-removal monitored hold is 7 days and the decommission authorization is signed by Kyle Manderfield (WMP). Essendis defines the residual-connection evidence check within that window.
G-50 | Exchange Decommission | The document states that after decommission, recipient management moves to "Entra ID Connect and PowerShell against Active Directory attributes" with no Exchange management server retained — but no runbook, tooling, or skills transfer is defined for that day-2 reality | WMP (8/25, via chat): Essendis is not providing runbooks for PowerShell-based management; WMP owns the processes. | Design update: post-decommission recipient management is WMP-owned. The design notes management continues via Entra Connect/PowerShell with no Essendis runbook deliverable.
G-51 | Operations & Support | The post-hypercare support model is explicitly undefined — the document states support channels "will be clearly defined during the hypercare period" and leaves escalation paths and response times blank | WMP operates the tenant after handoff (G-55). Hypercare will be available for the week following migration with 2hr response objective. Requests to come via email and teams. WMP handling user-facing support. | Support model set: hypercare runs one week post-migration with a 2-hour response objective; requests via email and Teams; WMP handles user-facing support thereafter. Essendis documents this in the Communications/support section.
G-52 | Operations & Support | There is no monitoring or alerting design | WMP (8/25, via chat): Operations and support are out of scope. Discovery (8/25): Arctic Wolf is the SIEM platform and will need visibility into the GCC High environment. | Scope decision: monitoring, alerting, and log-review design are out of engagement scope — WMP decides (an Azure subscription exists if Log Analytics is wanted). Essendis's remaining action is the G-03 cleanup: reword the design's break-glass 'Log Analytics in Azure' reference to reflect WMP-owned alerting.
G-53 | Operations & Support | Backup and recoverability for M365 data is not addressed | Backups out of scope. Discovery (8/25): ArcServe does not support GCC High; WMP is already evaluating replacement backup solutions (Asana action). | Scope decision: Microsoft 365 backup out of scope — native retention, versioning, and recycle bins accepted.
G-54 | Operations & Support | Recurring operational tasks are never listed | WMP owns all. | Ownership decision: WMP owns all recurring renewals and reviews after handoff (include the renewal list in handoff documentation per G-63).
G-55 | Operations & Support | There is no change control process for the tenant after go-live | WMP owns after handoff. | Ownership decision: WMP owns tenant change control after handoff.
G-56 | CUI Governance & Compliance | The CMMC assessment boundary is never defined | All out of scope. | Scope decision: CMMC boundary definition is out of this engagement's scope (RPO domain).
G-57 | CUI Governance & Compliance | There is no traceability between the design's settings and the CMMC/NIST SP 800-171 practices, in either direction: the RPO control mapping that WBS 2.1.1 makes a hard gate has not been received, and the evidence package and Solution Configuration Document that WBS 2.9 delivers have no defined format or maintainer | Essendis configuring all applicable M365 settings for control alignment using their approach and judgement - compliance is on the RPO and out of scope. | Scope decision: Essendis configures all applicable M365 settings using its own approach and judgment; compliance mapping and evidence are the RPO's responsibility.
G-58 | CUI Governance & Compliance | CUI information protection is undefined | WMP (8/24): CUI label is the only part of taxonomy in scope. Manual labeling. DLP should block. Endpoint DLP in scope. Communication compliance out of scope. | CUI protection: a single CUI sensitivity label, manually applied; DLP blocks on the CUI label across Exchange, Teams, SharePoint and OneDrive; Endpoint DLP in scope; Communication Compliance out of scope. Essendis proposes the label's marking/encryption behaviour and the endpoint restrictions (USB, print, clipboard) for WMP sign-off in the configuration document.
G-59 | CUI Governance & Compliance | Retention and disposition are defined only in fragments — OneDrive 7 years for leavers, Teams recordings 180 days, spam quarantine 14 days, SharePoint 500 versions | retention is out of scope. | Scope decision: organisation-wide retention design out of scope; the existing per-workload fragments stand.
G-60 | CUI Governance & Compliance | Audit logging is mentioned once, for Teams ("ensure audit logging is on") | Known from WBS 2.6.2: audit retention is set to meet a CMMC 90-day minimum | Audit logging enabled tenant-wide at initialization with mailbox auditing; retention meets the CMMC 90-day minimum (WBS 2.6.2). No extended export required.
G-61 | CUI Governance & Compliance | DFARS 252.204-7012 operational obligations are not designed | Out of scope | Scope decision: DFARS 7012 incident-response operations out of scope (SOC contact placeholders remain tracked in G-17).
G-62 | CUI Governance & Compliance | Only CallTower has a shared responsibility matrix | Out of scope - not handling compliance and Avepoint not handling CUI. | Scope decision: vendor SRM / flow-down collection out of scope; WMP position recorded: AvePoint does not handle CUI.
G-63 | Documentation & Handoff | The documentation deliverables and their acceptance are not stated in the design | Design Document, Configuration Document. WMP owns everything after handoff. | Decision: documentation set is the Solution Design Document plus the Configuration Document; WMP owns all documentation after handoff.
G-64 | Documentation & Handoff | The design contains no diagrams | No diagrams are in scope. | Scope decision: no diagrams in scope.

## Discovery Facts
# | Fact (discovery session, 8/25/2026)
1 | First discovery session with the client; prior work was a kickoff meeting only.
2 | Goal: a GCC High environment that upgrades and closely mirrors the current environment.
3 | Current licensing: Microsoft 365 Commercial with Business Standard and Business Basic.
4 | RSA addresses authentication requirements today and is retained for desktop MFA on-premises.
5 | Environment is predominantly on-premises; cloud workloads are limited to M365 email and an Epicor ERP hosted in Azure Government.
6 | All file storage is on-premises.
7 | FortiGate SSL VPN in use; M365 authentication integration desired after migration.
8 | On-premises PKI in place, used for device certificates and network access control.
9 | SSPR in M365 is of interest; other tools (Netwrix, ManageEngine) also being evaluated.
10 | User population heavily shop-floor; approximately 50 information workers.
11 | Exchange 2016 remains on-premises as a management platform only; mailboxes and mail flow migrated to M365 previously.
12 | Identities continue synchronizing from on-prem AD; the on-prem Exchange server should be eliminated.
13 | Devices sending email: printers, ERP systems, help-desk platform.
14 | SMTP relay requirements exist; TLS expected for supported devices.
15 | Pipedrive sends marketing/mailing-list communications via integration with the email platform.
16 | Calendar sharing exists with two sister organizations; free/busy sharing should be maintained if possible.
17 | External guest accounts are used primarily for SharePoint file sharing, not Teams collaboration.
18 | Kiteworks is used today for external CUI file exchange.
19 | Objective: replace Kiteworks with SharePoint for external file sharing.
20 | Five SharePoint sites confirmed for migration.
21 | Additional Teams/SharePoint sites are being evaluated by departments.
22 | Some Teams/SharePoint assets belong to M365 Groups; others were created independently.
23 | Three locations.
24 | Two locations currently provide guest wireless only.
25 | New third location under construction receives corporate Wi-Fi via RADIUS (NPS or ClearPass).
26 | Third-site occupancy began August 1; operational readiness targeted mid-November.
27 | Site-to-site VPN connectivity exists between locations.
28 | Each location connects to the Azure Government ERP environment.
29 | FortiClient EMS manages SSL VPN for remote workers.
30 | ~34 users use remote access; one employee is fully remote.
31 | Shared shop-floor PCs exist; moving away from shared credentials to individual sign-ins.
32 | ~40 shop-floor devices will require M365 access.
33 | Intended Windows management strategy: hybrid management with both AD and Intune.
34 | No corporate mobile devices today; deployment planned.
35 | Future mobile deployment expected under 40 devices, iOS and Android.
36 | BYOD will not be supported.
37 | Mobile apps: Outlook, Teams, OneDrive, RSA Authenticator, Keeper.
38 | Apple Business Manager and Google mobile management platforms not yet configured.
39 | Five conference rooms today; additional rooms planned at the new facility.
40 | Conference rooms use dedicated Windows devices or user laptops with existing AV equipment.
41 | No Teams Rooms deployment currently planned.
42 | Client can rapidly support discovery activities after receiving instructions.
43 | Custom discovery scripts require review before execution.
44 | ~20 PST archives (~50 GB combined) should be merged back into active mailboxes.
45 | No third-party email archive platform beyond backup solutions.
46 | ArcServe backups do not support GCC High; replacement solutions being evaluated.
47 | Azure Government ERP is managed by Epicor; the client has no direct Azure administrative access.
48 | Organization is tenant owner of record; Epicor is authorized reseller and manager.
49 | Preferred production email domain for GCC High: wisconsinmetalparts.com.
50 | Client is comfortable with a default onmicrosoft.us domain during setup.
51 | No applications authenticate through M365 today; long-term goal is Entra ID authentication for several apps.
52 | Third-party applications accessing M365 mailboxes/calendars: NinjaOne, Keeper, Fortra.
53 | Service accounts are primarily on-premises in a dedicated OU.
54 | All devices can be physically brought into the office for migration and encryption activities.
55 | NinjaOne is used for device management and software deployment.
56 | Application deployment continues through NinjaOne rather than Intune.
57 | Two print servers.
58 | Three file servers, reducing to two.
59 | File services available across all sites via VPN.
60 | DFS Namespaces not in use; standard UNC paths.
61 | Total file-share storage ~7 TB.
62 | Drive mappings deployed through Group Policy.
63 | Printer management remains GPO-based; Kyocera MyPrint under evaluation.
64 | Hybrid Azure AD Join remains the intended device strategy.
65 | Arctic Wolf is the current SIEM and needs visibility into GCC High.
66 | Multiple line-of-business applications authenticate directly against on-prem AD.
67 | Manufacturing systems and file services depend on Active Directory accounts.
68 | Cutover goal: mid-November (per M. Schraepfer, 8/25).
69 | Decommission sequencing in flux - leaning post-cutover.